## Sheet1 (5)
Starting Year | 2012
|  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Outcomes
Refocus
Developing marketing campaign for Welltory | bar: 2013 Q4 to 2014 Q1
Lauching online ad campaign for Welltory app | bar: 2014 Q2 to 2014 Q3
Ongoing promotions for loyal Welltory customers | bar: 2014 Q4 to 2016 Q4
Restructure
Building data team
Hire data leader for the org | bar: 2012 Q1 to 2012 Q2
Hire data science team of 10 people | bar: 2012 Q2 to 2012 Q4
Establish org structure around new data team | bar: 2013 Q1 to 2013 Q3
Welltory acqusition
Launch Welltory acquisition process | bar: 2012 Q3
Hire legal staff | bar: 2012 Q3
Complete acquisition | bar: 2012 Q4 to 2013 Q1
Begin onboarding | bar: 2013 Q2 to 2013 Q3
Launch Welltory data driven RnD focus platform | bar: 2013 Q4 to 2016 Q4
Refresh
Employee matching program
Develop partnership with menttium | bar: 2012 Q1 to 2012 Q3
Employee matching program start | bar: 2012 Q4
Ongoing employee matching initiative | bar: 2013 Q1 to 2016 Q4
School for Enterpreneurs
Develop online course content w Dosibo | bar: 2012 Q1 to 2012 Q3
Kickoff of online and in-person session | bar: 2012 Q4
Launch idea incubator + pitch competition | bar: 2013 Q1 to 2013 Q2
Implement winning ideas for the business | bar: 2013 Q3 to 2014 Q1
Ongoing KPIs tracking | bar: 2014 Q2 to 2016 Q4

## Sheet1 (6)
Starting Year | 2012
|  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Outcomes
Refocus | bar: 2012 Q1 to 2015 Q4
Developing marketing campaign for Welltory | bar: 2013 Q4 to 2014 Q1
Lauching online ad campaign for Welltory app | bar: 2014 Q2 to 2014 Q3
Ongoing promotions for loyal Welltory customers | bar: 2014 Q4 to 2016 Q4
Restructure | bar: 2012 Q1 to 2015 Q4
Building data team
Hire data leader for the org | bar: 2012 Q1 to 2012 Q2
Hire data science team of 10 people | bar: 2012 Q2 to 2012 Q4
Establish org structure around new data team | bar: 2013 Q1 to 2013 Q3
Welltory acqusition
Launch Welltory acquisition process | bar: 2012 Q3
Hire legal staff | bar: 2012 Q3
Complete acquisition | bar: 2012 Q4 to 2013 Q1
Begin onboarding | bar: 2013 Q2 to 2013 Q3
Launch Welltory data driven RnD focus platform | bar: 2013 Q4 to 2016 Q4
Refresh | bar: 2012 Q1 to 2015 Q4
Employee matching program
Develop partnership with menttium | bar: 2012 Q1 to 2012 Q3
Employee matching program start | bar: 2012 Q4
Ongoing employee matching initiative | bar: 2013 Q1 to 2016 Q4
School for Enterpreneurs
Develop online course content w Dosibo | bar: 2012 Q1 to 2012 Q3
Kickoff of online and in-person session | bar: 2012 Q4
Launch idea incubator + pitch competition | bar: 2013 Q1 to 2013 Q2
Implement winning ideas for the business | bar: 2013 Q3 to 2014 Q1
Ongoing KPIs tracking | bar: 2014 Q2 to 2016 Q4

## Sheet1 (7)
Starting Year | 2019
|  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Recruit
Employer Assisted Student-Loan Repayment
Develop partnership with Gradifi | bar: 2019 Q1 to 2019 Q3
Build out Gradifi benefits package for existing employees | bar: 2019 Q4 to 2020 Q2
Begin offering Gradifi to employees | bar: 2020 Q3 to 2023 Q4
NorthStar Career Planning Program
Develop partnership with Fuel50 CareerDrive | bar: 2019 Q1 to 2019 Q2
Hire career advisors | bar: 2019 Q1 to 2020 Q1
Build out infrastructure for career advising services | bar: 2019 Q3 to 2020 Q1
Begin offering career advising sessions | bar: 2020 Q2 to 2023 Q4
eNG Degree
Establish partnership with Stanford University | bar: 2019 Q1 to 2019 Q3
Develop program curriculum | bar: 2019 Q4 to 2020 Q2
Launch program at Stanford University | bar: 2020 Q3 to 2023 Q4
Continue expansion to Caltech University | bar: 2021 Q3 to 2023 Q4
Retain
Baseball card profiles
Build out profile infrastructure | bar: 2019 Q1 to 2019 Q2
Integrate baseball card profiles with Fuel50 | bar: 2019 Q3 to 2019 Q4
Build out general data aggregation pipelines | bar: 2020 Q1 to 2020 Q2
Knowledge trasfer with Fuel50 FuelPath
Develop partnership with Fuel50 FuelPath | bar: 2019 Q1 to 2019 Q2
Setup Fuel50 FuelPath software | bar: 2019 Q3 to 2019 Q4
Integrate with Baseball Card profiles | bar: 2020 Q1 to 2020 Q2
Ongoing employee knowledge transfer with Fuel50 FuelPath | bar: 2020 Q3 to 2023 Q4
Proactive turnover prevention program (PTPP)
Begin historical data collection | bar: 2019 Q3 to 2020 Q2
Build out turnover prediction algorithms | bar: 2020 Q3 to 2021 Q2
Expand career advising to predited employees | bar: 2021 Q3 to 2023 Q4
Reinvigorate
WorkOnWhatMatters Challenge
Develop competition guidelines and rules | bar: 2019 Q1 to 2019 Q2
Launch yearly competitions | bar: 2020 Q1; 2021 Q1; 2022 Q1; 2023 Q1
Expansion Area: LIDAR
Develop new business unit for LIDAR | bar: 2019 Q1 to 2020 Q2
Expansion Area: Drones in Asia
Develop new business unit for Health products delivery | bar: 2020 Q3 to 2021 Q4
|  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Recruit
Employer Assisted Student-Loan Repayment
Develop partnership with Gradifi | bar: 2019 Q1 to 2020 Q2
Begin offering Gradifi to employees | bar: 2020 Q3 to 2023 Q4
NorthStar Career Planning Program
Develop partnership with Fuel50 CareerDrive | bar: 2019 Q1 to 2019 Q2
Hire career advisors | bar: 2019 Q1 to 2020 Q1
Begin offering career advising sessions | bar: 2020 Q2 to 2023 Q4
eNG Degree
Establish partnership with Stanford University | bar: 2019 Q1 to 2020 Q2
Launch program at Stanford University | bar: 2020 Q3 to 2023 Q4
Continue expansion to Caltech University | bar: 2021 Q3 to 2023 Q4
Retain
Baseball card profiles
Build out profile infrastructure | bar: 2019 Q1 to 2019 Q4
Build out general data aggregation pipelines | bar: 2020 Q1 to 2020 Q2
Knowledge trasfer with Fuel50 FuelPath
Develop partnership with Fuel50 FuelPath | bar: 2019 Q1 to 2019 Q2
Setup Fuel50 FuelPath software | bar: 2019 Q3 to 2020 Q2
Ongoing employee knowledge transfer with Fuel50 FuelPath | bar: 2020 Q3 to 2023 Q4
Proactive turnover prevention program (PTPP)
Begin historical data collection | bar: 2019 Q3 to 2020 Q2
Build out turnover prediction algorithms | bar: 2020 Q3 to 2021 Q2
Expand career advising to predited employees | bar: 2021 Q3 to 2023 Q4
Reinvigorate
WorkOnWhatMatters Challenge
Develop competition guidelines and rules | bar: 2019 Q1 to 2019 Q2
Launch yearly competitions | bar: 2020 Q1; 2021 Q1; 2022 Q1; 2023 Q1
Expansion Area: LIDAR | bar: 2019 Q1 to 2020 Q2
Expansion Area: Drones in Asia | bar: 2020 Q3 to 2021 Q4

## Sheet1 (4)
Starting Year | 2012
|  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Outcomes
Refocus | bar: 2012 Q1 to 2015 Q4
Developing marketing campaign for Welltory | bar: 2013 Q4 to 2014 Q1
Lauching online ad campaign for Welltory app | bar: 2014 Q2 to 2014 Q3
Ongoing promotions for loyal Welltory customers | bar: 2014 Q4 to 2016 Q4
Restructure | bar: 2012 Q1 to 2015 Q4
Building data team
Hire data leader for the org | bar: 2012 Q1 to 2012 Q2
Hire data science team of 10 people | bar: 2012 Q2 to 2012 Q4
Establish org structure around new data team | bar: 2013 Q1 to 2013 Q3
Welltory acqusition
Launch Welltory acquisition process | bar: 2012 Q3
Hire legal staff | bar: 2012 Q3
Complete acquisition | bar: 2012 Q4 to 2013 Q1
Begin onboarding | bar: 2013 Q2 to 2013 Q3
Launch Welltory data driven RnD focus platform | bar: 2013 Q4 to 2016 Q4
Refresh | bar: 2012 Q1 to 2015 Q4
Employee matching program
Develop partnership with menttium | bar: 2012 Q1 to 2012 Q3
Employee matching program start | bar: 2012 Q4
Ongoing employee matching initiative | bar: 2013 Q1 to 2016 Q4
School for Enterpreneurs
Develop online course content w Dosibo | bar: 2012 Q1 to 2012 Q3
Kickoff of online and in-person session | bar: 2012 Q4
Launch idea incubator + pitch competition | bar: 2013 Q1 to 2013 Q2
Implement winning ideas for the business | bar: 2013 Q3 to 2014 Q1
Ongoing KPIs tracking | bar: 2014 Q2 to 2016 Q4

## Sheet1
Starting Year | 2012
|  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Refocus
Developing marketing campaign for Welltory | bar: 2013 Q4 to 2014 Q1
Lauching online ad campaign for Welltory app | bar: 2014 Q2 to 2014 Q3
Ongoing promotions for loyal Welltory customers | bar: 2014 Q4 to 2016 Q4
Restructure
Building data team
Hire data leader for the org | bar: 2012 Q1 to 2012 Q2
Hire data science team of 10 people | bar: 2012 Q2 to 2012 Q4
Establish org structure around new data team | bar: 2013 Q1 to 2013 Q3
Welltory acqusition
Launch Welltory acquisition process | bar: 2012 Q3
Hire legal staff | bar: 2012 Q3
Complete acquisition | bar: 2012 Q4 to 2013 Q1
Begin onboarding | bar: 2013 Q2 to 2013 Q3
Launch Welltory data driven RnD focus platform | bar: 2013 Q4 to 2016 Q4
Refresh
Employee matching program
Develop partnership with menttium | bar: 2012 Q1 to 2012 Q3
Employee matching program start | bar: 2012 Q4
Ongoing employee matching initiative | bar: 2013 Q1 to 2016 Q4
School for Enterpreneurs
Develop online course content w Dosibo | bar: 2012 Q1 to 2012 Q3
Kickoff of online and in-person session | bar: 2012 Q4
Launch idea incubator + pitch competition | bar: 2013 Q1 to 2013 Q2
Implement winning ideas for the business | bar: 2013 Q3 to 2014 Q1
Ongoing KPIs tracking | bar: 2014 Q2 to 2016 Q4