## timeline
Starting Year | 2019
|  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Recruit
Employer Assisted Student-Loan Repayment
Develop partnership with Gradifi | bar: 2019 Q1 to 2019 Q3
Build out Gradifi benefits package for existing employees | bar: 2019 Q4 to 2020 Q2
Begin offering Gradifi to employees | bar: 2020 Q3 to 2023 Q4
NorthStar Career Planning Program
Develop partnership with Fuel50 CareerDrive | bar: 2019 Q1 to 2019 Q2
Hire career advisors | bar: 2019 Q1 to 2020 Q1
Build out infrastructure for career advising services | bar: 2019 Q3 to 2020 Q1
Begin offering career advising sessions | bar: 2020 Q2 to 2023 Q4
eNG Degree
Establish partnership with Stanford University | bar: 2019 Q1 to 2019 Q3
Develop program curriculum | bar: 2019 Q4 to 2020 Q2
Launch program at Stanford University | bar: 2020 Q3 to 2023 Q4
Continue expansion to Caltech University | bar: 2021 Q3 to 2023 Q4
Retain
Baseball card profiles
Build out profile infrastructure | bar: 2019 Q1 to 2019 Q2
Integrate baseball card profiles with Fuel50 | bar: 2019 Q3 to 2019 Q4
Build out general data aggregation pipelines | bar: 2020 Q1 to 2020 Q2
Knowledge trasfer with Fuel50 FuelPath
Develop partnership with Fuel50 FuelPath | bar: 2019 Q1 to 2019 Q2
Setup Fuel50 FuelPath software | bar: 2019 Q3 to 2019 Q4
Integrate with Baseball Card profiles | bar: 2020 Q1 to 2020 Q2
Ongoing employee knowledge transfer with Fuel50 FuelPath | bar: 2020 Q3 to 2023 Q4
Proactive turnover prevention program (PTPP)
Begin historical data collection | bar: 2019 Q3 to 2020 Q2
Build out turnover prediction algorithms | bar: 2020 Q3 to 2021 Q2
Expand career advising to predited employees | bar: 2021 Q3 to 2023 Q4
Reinvigorate
WorkOnWhatMatters Challenge
Develop competition guidelines and rules | bar: 2019 Q1 to 2019 Q2
Launch yearly competitions | bar: 2020 Q1; 2021 Q1; 2022 Q1; 2023 Q1
Expansion Area: LIDAR
Develop new business unit for LIDAR | bar: 2019 Q1 to 2020 Q2
Expansion Area: Drones in Asia
Develop new business unit for Health products delivery | bar: 2020 Q3 to 2021 Q4